## 📋 Overview
🏫 SHIKSHA PORTAL — MVP Product Roadmap
Village School Education Platform ¦ Solo Developer ¦ Hindi + English ¦ Target: 6-Week MVP Build + Deployment
Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | 🚀 Deploy Week 4
Week 1-2 |  |  | Week 2-3 |  |  | Week 3-4
Foundation + Auth |  |  | Core Features |  |  | AI + Bilingual + Polish
Epic / Module | Sprint | Priority | Story Points | Status | Description | Acceptance Criteria | Data Required | Tech Stack | Owner
1. Multi-Tenant Setup | Sprint 1 | 🔴 Critical | 8 | ⬜ Todo | Rails app configured for multi-tenancy. Each school gets its own subdomain (e.g. greenvalley.shikshaportal.in) | • School A data not visible to School B • Subdomain routes to correct school • Wildcard DNS resolves correctly | • School name • Subdomain slug • Admin email • School address | Rails + acts_as_tenant gem + Nginx wildcard + Cloudflare DNS | Dev
2. School Registration | Sprint 1 | 🔴 Critical | 5 | ⬜ Todo | Super admin (you) can register a new school. School gets its own subdomain and admin login instantly. | • School created in DB • Subdomain live within 1 min • Admin receives login email • School logo uploadable | • School name, address, phone • Principal name + email • School logo (image) • Board (CBSE/State/Other) | Rails API + ActiveStorage + Resend email + Cloudflare R2 | Dev
3. Authentication (3 Roles) | Sprint 1 | 🔴 Critical | 8 | ⬜ Todo | Three login roles: Super Admin (you), School Admin (principal/teacher), Student. Each sees different dashboard. | • Login works per subdomain • Role-based dashboard shown • JWT token + session secure • Password reset via email | • User email • Hashed password • Role (super_admin/school_admin/student) • School tenant ID | Devise + JWT + Rails + React Auth Context | Dev
4. School Public Page | Sprint 1 | 🟡 High | 5 | ⬜ Todo | Each school gets a public-facing page (their 'website'). Shows school info, notice board, contact. No login needed to view. | • Page live on school subdomain • School logo/name/address shown • Latest 5 notices visible • Mobile responsive | • School name, logo, address • Phone, email • About us text • Notices (from notice module) | React + Tailwind CSS + Rails API (public endpoints) | Dev
5. Student Management | Sprint 1 | 🟡 High | 5 | ⬜ Todo | School admin can add students one by one or bulk upload via CSV. Each student gets auto-generated login credentials. | • Add single student form works • CSV bulk upload works (100+ students) • Student login credentials emailed • Students listed with class/section filter | • Student name • Class + Section • Parent phone number • Student email (optional) • Roll number | Rails + CSV parsing + ActiveRecord + Resend email | Dev
6. Notice Board | Sprint 2 | 🟡 High | 5 | ⬜ Todo | Admin posts notices/announcements. Students see them on login dashboard and on public school page. | • Admin can create/edit/delete notice • Notice shows date + title + body • Students see notices on dashboard • Public page shows latest 5 | • Notice title • Notice body (text) • Posted date • Posted by (admin name) • School tenant ID | Rails API + React + ActionText (rich text) | Dev
7. Study Material Upload | Sprint 2 | 🟡 High | 5 | ⬜ Todo | Admin uploads PDF study materials per class/subject. Students download from their dashboard. | • PDF upload works (max 10MB) • Files organised by class + subject • Student can only see their class materials • Download button works | • File (PDF) • Subject name • Class/grade • Upload date • Uploader admin ID • School tenant ID | Rails + ActiveStorage + Cloudflare R2 + React | Dev
8. Attendance Marking | Sprint 2 | 🟡 High | 8 | ⬜ Todo | Admin/teacher marks daily attendance per class. Students can view their own attendance record and percentage. | • Mark present/absent per student per day • Cannot mark future dates • Student sees own attendance % • Admin sees class-wise report | • Student ID • Date • Status (Present/Absent/Leave) • Class + Section • Marked by (admin ID) • School tenant ID | Rails API + React date-picker + PostgreSQL | Dev
9. Fee Record Management | Sprint 2 | 🟡 High | 8 | ⬜ Todo | Admin records fee payments manually. Generate printable receipt. Student sees fee status (paid/due). | • Record payment with amount + date • Generate PDF receipt • Student sees payment history • Filter by paid/unpaid | • Student ID • Amount paid • Payment date • Fee type (tuition/exam/other) • Receipt number (auto) • School tenant ID | Rails + Prawn gem (PDF receipt) + React + PostgreSQL | Dev
10. Student Dashboard | Sprint 2 | 🟡 High | 5 | ⬜ Todo | Student login shows personalised dashboard: notices, materials for their class, attendance %, fee status. | • Shows student name + class • Latest 5 notices visible • Materials for own class only • Attendance % shown • Fee status shown | • Student profile data • Tenant-scoped notices • Class-filtered materials • Attendance records • Fee records | React + Rails API (tenant-scoped endpoints) | Dev
11. AI Parent Communicator | Sprint 2 | 🔴 Critical | 5 | ⬜ Todo | Admin types rough Hindi/English → AI generates formal school notice + WhatsApp-ready parent message. One-click post to notice board or copy for WhatsApp. | • Hindi + English input works • Notice + WhatsApp message in <5 seconds • Admin can edit before posting • One-click post to notice board • Copy-for-WhatsApp button • Optional bilingual output (Hindi + English) | • Admin rough input text • School name (context) • Category (holiday/fee/exam/event) • Language preference • Claude API prompt template | Claude Haiku API + Rails endpoint + React modal + prompt engineering | Dev
12. Bilingual UI (Hindi + English) | Sprint 1 | 🔴 Critical | 5 | ⬜ Todo | Full website UI in Hindi and English. Language toggle in header. Hindi default for school tenants. Noto Sans Devanagari font. Emails sent in user language preference. | • हिंदी ¦ English toggle on all screens • Hindi default on school subdomains • Login, dashboard, nav fully translated • Language saved in localStorage + user profile • Devanagari font renders correctly on mobile • Welcome emails in preferred language | • en/hi locale JSON files • language_preference on users • default_language on schools • Google Fonts Noto Sans Devanagari | react-i18next + Rails I18n + locale JSON files + Noto Sans Devanagari | Dev
13. Admin Dashboard | Sprint 3 | 🟡 High | 5 | ⬜ Todo | School admin home screen shows key stats: total students, today's attendance %, pending fees, recent notices. | • Total student count shown • Today's attendance % shown • Count of unpaid fees shown • Last 3 notices shown • Quick-action buttons | • Aggregated student count • Today's attendance records • Unpaid fee count • Recent notices • All scoped to tenant | Rails API (aggregate queries) + React dashboard components | Dev
14. Deployment + Infrastructure | Sprint 3 | 🔴 Critical | 8 | ⬜ Todo | Full production deployment: Oracle Cloud server, Neon DB, Cloudflare R2, Cloudflare wildcard SSL, Sidekiq+Redis, CI/CD pipeline. | • App live on production URL • Wildcard HTTPS via Cloudflare (no Certbot) • GitHub Actions auto-deploy on push • Uptime monitoring active • DB backups configured (Neon branches) • Sidekiq processing async jobs | • Oracle Cloud account • Cloudflare account + domain • Neon.tech DB URL • Resend API key • Claude API key • GitHub repository | Oracle Cloud + Nginx + Puma + Cloudflare SSL + GitHub Actions + UptimeRobot + Neon + R2 + Redis | Dev

## 🗂 Sprint Tasks
🗂 Sprint Task Breakdown — Story-Level Detail
# | Task Name | Epic | Sprint | Priority | Est. Hours | Description | Data Needed | Acceptance Criteria | Dependencies
T01 | Setup Rails API project + PostgreSQL | Multi-Tenant | Sprint 1 | 🔴 Critical | 4h | Initialise Rails API-only app, configure PostgreSQL, setup Gemfile with required gems | • Ruby version • PostgreSQL credentials • App name decision | • Rails app boots • DB connection works • Git repo initialised | None — first task
T02 | Configure acts_as_tenant gem | Multi-Tenant | Sprint 1 | 🔴 Critical | 6h | Install and configure multi-tenancy. Every DB query auto-scoped to current school tenant via subdomain | • Tenant model schema • Subdomain routing logic | • School A cannot see School B data • Subdomain correctly identifies tenant • Test with 2 dummy schools | T01
T03 | Nginx + wildcard subdomain config | Multi-Tenant | Sprint 1 | 🔴 Critical | 5h | Configure Nginx on Oracle Cloud server to route *.shikshaportal.in to Rails app. HTTPS via Cloudflare Full (strict) — no Certbot needed on server. | • Domain name purchased • Cloudflare DNS wildcard A record • Oracle server IP | • Any subdomain resolves to app • HTTPS works via Cloudflare edge SSL • Origin cert or self-signed on Nginx • Cloudflare proxy enabled (orange cloud) | T01, Domain purchased
T04 | School registration API + form | School Registration | Sprint 1 | 🔴 Critical | 6h | Super admin panel to create a new school. Auto-creates tenant, subdomain entry, and admin user | • School model fields • Admin user model fields • Email template for welcome | • POST /api/schools creates school • Subdomain entry created • Admin login email sent | T02, T03
T05 | Devise + JWT authentication | Authentication | Sprint 1 | 🔴 Critical | 8h | Setup Devise for user auth. JWT tokens for React SPA. Role-based access: super_admin, school_admin, student | • User roles defined • JWT secret key • Token expiry time | • Login returns JWT • Role decoded from token • Unauthorised returns 401 • Password reset email works | T04
T06 | React project setup + auth flow | Authentication | Sprint 1 | 🔴 Critical | 6h | Create React app, configure Axios for API calls, build Login page, store JWT in memory, role-based routing | • API base URL • Role definitions • Route structure plan | • Login page works • JWT stored securely • Redirects by role • Subdomain-aware API calls | T05
T07 | School public page (React) | School Public Page | Sprint 1 | 🟡 High | 6h | Build the public-facing school page. No login required. Shows school info, logo, contact, latest notices | • School profile data • Public API endpoints • Design (logo, colors) | • Page loads without login • School logo displayed • Latest 5 notices shown • Mobile responsive | T04, T06
T08 | Student bulk import (CSV) | Student Management | Sprint 1 | 🟡 High | 6h | Admin uploads CSV of students. System creates student accounts, sends login credentials via email | • CSV column format defined • Student model schema • Email template for credentials | • CSV with 100 rows processed • Duplicate roll numbers flagged • Login emails sent • Error rows reported | T05
T09 | Notice CRUD API + React UI | Notice Board | Sprint 2 | 🟡 High | 6h | Admin creates/edits/deletes notices. Student dashboard and public page display them | • Notice model schema • Tenant scoping confirmed • Rich text or plain text decision | • Create/edit/delete works • Notices tenant-scoped • Student sees only own school notices • Ordered by date desc | T05, T06
T10 | File upload to Cloudflare R2 | Study Materials | Sprint 2 | 🟡 High | 6h | Configure ActiveStorage with Cloudflare R2. Admin uploads PDFs per class/subject. Students download. | • R2 bucket name • R2 access key + secret • File size limit decision • Subject list | • PDF uploads to R2 • Download link works • Files scoped by class • Student sees only own class | T05, T06
T11 | Attendance marking system | Attendance | Sprint 2 | 🟡 High | 8h | Admin marks daily attendance per class. Bulk mark (all present, then uncheck absents). Student views own record | • Attendance model schema • Date handling (IST timezone) • Class/section structure | • Mark attendance for full class in <2 min • Cannot mark future dates • Student sees % and history • Admin sees class report | T08
T12 | Fee recording + PDF receipt | Fee Management | Sprint 2 | 🟡 High | 8h | Admin records fee payment. System generates PDF receipt using Prawn gem. Student sees payment history | • Fee types list • Receipt number format • School bank details (for receipt) • Prawn gem installed | • Fee entry saved • PDF receipt downloads • Receipt has school logo + details • Student sees paid/unpaid status | T08
T13 | Student dashboard (React) | Student Dashboard | Sprint 2 | 🟡 High | 6h | Personalised student home screen after login. Shows notices, class materials, attendance %, fee status | • All Sprint 2 APIs complete • Student profile data • Class/section assignment | • Dashboard loads in <2s • All 4 sections shown • Data is student-specific • Mobile responsive | T09, T10, T11, T12
T14 | Admin dashboard (React) | Admin Dashboard | Sprint 3 | 🟡 High | 6h | School admin home screen with key stats: student count, today's attendance %, fee summary, recent notices | • Aggregate query APIs • Stats calculation logic | • Stats load correctly • Quick-action buttons work • Mobile responsive • Refreshes on new data | T09, T10, T11, T12
T15 | AI Parent Communicator | AI Feature | Sprint 2 | 🔴 Critical | 6h | Admin types rough Hindi/English idea → Claude Haiku generates formal notice + WhatsApp parent message. Category picker (holiday/fee/exam/event). One-click post or copy. | • Claude API key • Prompt template • Category types • Bilingual output toggle • Daily usage cap (50/day MVP) | • Response in <5 seconds • Notice title + body generated • WhatsApp message generated • Admin can edit before posting • One-click post to notice board • Copy-for-WhatsApp button works | T09
T16 | GitHub Actions CI/CD pipeline | Deployment | Sprint 3 | 🔴 Critical | 5h | Auto-deploy to Oracle Cloud on git push to main branch. Run tests, build React, restart Rails server | • Oracle server SSH key • Server IP • Deploy script • Environment variables list | • Push to main triggers deploy • Tests run before deploy • Failed tests block deploy • Slack/email on deploy | T03
T17 | Environment config + secrets | Deployment | Sprint 3 | 🔴 Critical | 3h | Setup all production environment variables securely. No secrets in codebase. Use Rails credentials or .env | • All API keys list • DB URL • R2 credentials • JWT secret • Resend API key | • No secrets in Git • App runs with env vars • Credentials documented (privately) • Staging env separate | T01
T18 | Production smoke testing | Deployment | Sprint 3 | 🔴 Critical | 4h | End-to-end test on production: register school → add students → AI notice → student logs in in Hindi → switch to English → verify all flows. | • Test school data • Test student accounts • All features complete | • Full user journey works on prod • No console errors • Mobile tested • Load test with 50 students | All tasks complete
T19 | Setup react-i18next + locale files | Bilingual UI | Sprint 1 | 🔴 Critical | 3h | Install react-i18next. Create en/ and hi/ locale JSON files for common, auth, dashboard modules. Wire i18n provider in React app. | • Locale file structure plan • Key screens list (P0) • Default language decision | • i18n provider wraps app • en + hi JSON files created • t() function works in components • Default locale: hi for schools | T06
T20 | Hindi font + translate P0 screens | Bilingual UI | Sprint 1 | 🔴 Critical | 8h | Add Noto Sans Devanagari via Google Fonts. Translate all P0 screens: login, nav, student dashboard, admin menu, attendance, notices, fees labels. | • Hindi translations for all P0 UI strings • Font loading strategy • Mobile font test plan | • Devanagari renders on Android phones • All P0 screens have hi + en strings • No missing translation keys in console • Text readable on small screens | T19
T21 | Language toggle + persistence | Bilingual UI | Sprint 1 | 🔴 Critical | 2h | Header toggle: हिंदी ¦ English. Persist in localStorage. Sync with user.language_preference on login. School default_language sets initial locale. | • localStorage key name • User language_preference field • School default_language field | • Toggle switches all UI instantly • Choice persists across sessions • Logged-in users sync preference to DB • School subdomain defaults to Hindi | T19, T05
T22 | Rails I18n for emails + API errors | Bilingual UI | Sprint 1 | 🟡 High | 2h | Setup Rails config/locales/hi.yml and en.yml. Welcome emails, password reset, and API error messages sent in user language_preference. | • hi.yml + en.yml email templates • I18n.with_locale wrapper • Error message keys | • Welcome email in Hindi for hi users • Password reset email bilingual • API errors return localized message • I18n.locale set from JWT/header | T05, T21
T23 | Sidekiq + Redis for async jobs | Infrastructure | Sprint 2 | 🟡 High | 4h | Install Sidekiq + Redis on Oracle VM. Async: CSV student import, welcome emails, AI API calls, PDF receipt generation. | • Redis install on VM • Sidekiq gem config • Job queue names • sidekiq.yml config | • CSV import runs in background • Emails sent async (no request timeout) • Sidekiq dashboard accessible (admin only) • Failed jobs retry 3 times | T01, T08

## 🗄 Data Models
🗄 Database Models & Data Dictionary
School (Tenant) (table: schools)
Column | Data Type | Constraints | Allowed Values | Notes
id | integer | PK |  | Auto-generated primary key
name | string | NOT NULL |  | Official school name
subdomain | string | UNIQUE NOT NULL |  | e.g. 'greenvalley' for greenvalley.shikshaportal.in
address | text |  |  | Full address of school
phone | string |  |  | Contact number
logo_url | string |  |  | Cloudflare R2 URL for school logo
board | string |  | CBSE/State/ICSE | Education board
default_language | string | NOT NULL | hi / en | Default UI language for school tenant. Default: hi
created_at | datetime | NOT NULL |  | Auto
updated_at | datetime | NOT NULL |  | Auto
User (All Roles) (table: users)
Column | Data Type | Constraints | Allowed Values | Notes
id | integer | PK
school_id | integer | FK → schools |  | Null for super_admin
name | string | NOT NULL |  | Full name
email | string | UNIQUE NOT NULL |  | Login email
encrypted_password | string | NOT NULL |  | Devise hashed
role | string | NOT NULL | super_admin / school_admin / student
class_name | string |  | e.g. '8th' | Students only
section | string |  | e.g. 'A' | Students only
roll_number | string |  |  | Students only
parent_phone | string |  | 10-digit mobile | Students only — for WhatsApp communication
language_preference | string | NOT NULL | hi / en | UI + email language. Default: hi
created_at | datetime | NOT NULL |  | Auto
Notice (table: notices)
Column | Data Type | Constraints | Allowed Values | Notes
id | integer | PK
school_id | integer | FK → schools NOT NULL |  | Tenant scope
title | string | NOT NULL |  | Short title
body | text | NOT NULL |  | Full notice content
posted_by_id
created_at | datetime | NOT NULL
Study Material (table: study_materials)
Column | Data Type | Constraints | Allowed Values | Notes
id | integer | PK
school_id | integer | FK → schools NOT NULL |  | Tenant scope
title | string | NOT NULL |  | e.g. 'Chapter 3 Notes'
subject | string | NOT NULL |  | e.g. 'Mathematics'
class_name | string | NOT NULL |  | e.g. '8th'
file_url | string | NOT NULL |  | Cloudflare R2 URL
uploaded_by_id
created_at | datetime | NOT NULL
Attendance (table: attendances)
Column | Data Type | Constraints | Allowed Values | Notes
id | integer | PK
school_id | integer | FK → schools NOT NULL |  | Tenant scope
student_id | integer | FK → users NOT NULL |  | Must be role=student
date | date | NOT NULL |  | Attendance date
status | string | NOT NULL | present/absent/leave
marked_by_id
created_at | datetime | NOT NULL
Fee Payment (table: fee_payments)
Column | Data Type | Constraints | Allowed Values | Notes
id | integer | PK
school_id | integer | FK → schools NOT NULL |  | Tenant scope
student_id | integer | FK → users NOT NULL
amount | decimal | NOT NULL |  | In INR
fee_type | string | NOT NULL | tuition/exam/other
paid_on | date | NOT NULL
receipt_number | string | UNIQUE NOT NULL |  | Auto-generated
created_at | datetime | NOT NULL
Database Indexes (Performance + Data Integrity)
Index / Constraint | Table | Columns |  | Notes
UNIQUE | users | school_id, roll_number |  | Prevent duplicate roll numbers per school
UNIQUE | attendances | school_id, student_id, date |  | Prevent double attendance entry
INDEX | notices | school_id, created_at |  | Fast notice listing
INDEX | study_materials | school_id, class_name |  | Fast material filtering
INDEX | fee_payments | school_id, student_id |  | Fast fee history lookup

## 🚀 Deployment
🚀 Deployment Checklist & Infrastructure Setup
# | Step | Service | Cost | Action / Command | Done?
PHASE 1 — DOMAIN & DNS
D01 | Purchase .in domain | Namecheap | ₹700/yr | Go to namecheap.com → search domain → buy .in | ☐
D02 | Add domain to Cloudflare | Cloudflare | Free | cloudflare.com → Add site → enter domain → update nameservers at Namecheap | ☐
D03 | Add wildcard A record | Cloudflare DNS | Free | DNS → Add record → Type: A, Name: *, Value: <Oracle server IP> | ☐
D04 | Enable wildcard SSL | Cloudflare SSL | Free | SSL/TLS → Full (strict) → Origin Server cert (Cloudflare origin cert or self-signed). NO Certbot needed. | ☐
PHASE 2 — SERVER SETUP
D05 | Create Oracle Cloud account | Oracle Cloud | Free | cloud.oracle.com → Sign up → verify card (no charge) | ☐
D06 | Create Always Free VM | Oracle Cloud | Free | Compute → Instances → Create → choose Ampere ARM → Always Free shape | ☐
D07 | SSH into server | Terminal | Free | ssh -i <key.pem> ubuntu@<server-ip> | ☐
D08 | Install Ruby + Rails | Oracle VM | Free | sudo apt update && sudo apt install rbenv ruby-build → rbenv install 3.2.0 | ☐
D09 | Install Node.js + Yarn | Oracle VM | Free | curl -fsSL https://deb.nodesource.com/setup_20.x ¦ sudo bash - && sudo apt install nodejs | ☐
D10 | Install Nginx + Puma | Oracle VM | Free | sudo apt install nginx → configure Puma systemd service → Nginx reverse proxy to Puma | ☐
D11 | Configure Nginx for wildcard | Oracle VM | Free | server_name *.shikshaportal.in; → nginx -t && systemctl reload nginx | ☐
PHASE 3 — DATABASE & STORAGE
D12 | Create Neon.tech account | Neon.tech | Free | neon.tech → Sign up → New project → copy DATABASE_URL | ☐
D13 | Create Cloudflare R2 bucket | Cloudflare R2 | Free | Cloudflare → R2 → Create bucket → name: shiksha-files → copy credentials | ☐
D14 | Create Resend account + API key | Resend.com | Free | resend.com → Sign up → API Keys → Create → verify sending domain | ☐
D15 | Get Claude API key | Anthropic | Pay-per-use | console.anthropic.com → API Keys → Create key → save securely | ☐
PHASE 4 — APP CONFIGURATION
D16 | Set Rails credentials/env vars | Oracle VM | Free | EDITOR=nano rails credentials:edit → add all keys → never commit plaintext | ☐
D17 | Run DB migrations on production | Oracle VM | Free | RAILS_ENV=production rails db:migrate | ☐
D18 | Precompile React build | Oracle VM | Free | cd frontend && npm run build → copy /dist to Rails public/ folder | ☐
D19 | Create super admin account | Rails console | Free | rails console → User.create!(email:..., role: 'super_admin', password:...) | ☐
PHASE 5 — CI/CD & MONITORING
D20 | Create GitHub Actions workflow | GitHub | Free | Add .github/workflows/deploy.yml → SSH deploy on push to main | ☐
D21 | Add server SSH key to GitHub secrets | GitHub | Free | Settings → Secrets → DEPLOY_KEY, SERVER_IP, SERVER_USER | ☐
D22 | Setup UptimeRobot monitor | UptimeRobot | Free | uptimerobot.com → Add monitor → URL: shikshaportal.in → alert: WhatsApp/email | ☐
D23 | Test full deployment pipeline | GitHub | Free | Push a small change → verify GitHub Actions runs → verify live site updated | ☐
PHASE 6 — GO LIVE CHECKS
D24 | Register first test school | App | Free | Visit shikshaportal.in/admin → register school → verify subdomain works | ☐
D25 | Add test students + mark attendance | App | Free | Upload CSV → mark attendance → verify student login shows data | ☐
D26 | Test AI Parent Communicator | App | API cost | Admin panel → type rough Hindi text → verify notice + WhatsApp message → post to board → copy WhatsApp | ☐
D27 | Mobile responsiveness test | Browser | Free | Open on mobile → test all screens → fix any layout issues | ☐
D28 | Share with first real school (pilot) | Real World | Free | Visit school physically → demo on laptop → onboard as free pilot | ☐
D29 | Install Redis + Sidekiq | Oracle VM | Free | sudo apt install redis-server → gem install sidekiq → configure systemd for Sidekiq worker | ☐
D30 | Setup Neon DB backup branch | Neon.tech | Free | Neon dashboard → Branches → create weekly backup branch → document restore steps | ☐
D31 | Add Noto Sans Devanagari font | Google Fonts | Free | Add fonts.googleapis.com link in React index.html → test Hindi on mobile browser | ☐
D32 | Test Hindi + English UI toggle | Browser | Free | Switch हिंदी ↔ English on all screens → verify no missing keys → test on mobile | ☐

## 💰 Cost Plan
💰 Infrastructure Cost Plan — Year 1
Service | Type | Monthly Cost | Year 1 Cost | Notes
Namecheap .in Domain | One-time | ₹58 (avg) | ₹700 | Renew yearly
Oracle Cloud VM (ARM) | Server | ₹0 | ₹0 | Always Free — permanent
Neon.tech PostgreSQL | Database | ₹0 | ₹0 | Free up to 3GB
Cloudflare R2 Storage | File Storage | ₹0 | ₹0 | Free up to 10GB
Cloudflare CDN + SSL + DNS | Network | ₹0 | ₹0 | Free forever
Resend.com Email | Email | ₹0 | ₹0 | 3,000 emails/month free
Claude Haiku API | AI | ₹250 | ₹3,000 | AI Parent Communicator — ~50 generations/day across all schools (~₹0.10/generation)
UptimeRobot Monitoring | Monitoring | ₹0 | ₹0 | Free tier
GitHub Actions CI/CD | DevOps | ₹0 | ₹0 | 2,000 min/month free
TOTAL — Year 1 |  | ~₹308/month | ~₹4,396/year
Break-Even Analysis
School pricing | ₹299/month per school
Schools needed to cover infra | 2 schools | Just 2 paying schools = infra paid
Revenue at 10 schools | ₹2,990/month | Profit: ₹2,682/month
Revenue at 50 schools | ₹14,950/month | Profit: ₹14,642/month
Revenue at 100 schools | ₹29,900/month
Scaling Triggers (When to Upgrade)
Trigger | Action | Est. Monthly Cost
Neon DB > 3GB or slow queries | Upgrade Neon paid tier | ₹1,500–3,000
Email > 3,000/month (bulk onboarding) | Resend paid plan | Usage-based
VM CPU consistently > 80% | Upgrade Oracle or add Hetzner VM (~€4) | ₹350–700
R2 storage > 10GB (many PDFs) | R2 paid storage | ₹50–200
AI > 200 generations/day | Review Claude usage + caching | ₹500–1,500